# The Rufford Small Grants Foundation

Final Report

---------------------------------------------------------------------------------------------------------------------------

Congratulations on the completion of your project that was supported by The Rufford Small Grants Foundation.

We ask all grant recipients to complete a Final Report Form that helps us to gauge the success of our grant giving. We understand that projects often do not follow the predicted course but knowledge of your experiences is valuable to us and others who may be undertaking similar work. Please be as honest as you can in answering the questions – remember that negative experiences are just as valuable as positive ones if they help others to learn from them.

Please complete the form in English and be as clear and concise as you can. We will ask for further information if required. If you have any other materials produced by the project, particularly a few relevant photographs, please send these to us separately.

Please submit your final report to jane@rufford.org. Thank you for your help.

## Josh Cole Grants Director

| Grant Recipient Details |  |
| --- | --- |
| Your name | Peter G. Mulbah |
| Project title | Environmental Conservation Outreach Programme Focusing on Youths around the East Nimba Nature Reserve (ENNR), Nimba County, Liberia. |
| RSG reference | 42.07.07 |
| Reporting period | February 2008 – February 2009 |
| Amount of grant | £4933 |
| Your email address | Sads_inc@yahoo.com/ director@sadsliberia.org |
| Date of this report | 2009-02-11 |

## Please indicate the level of achievement of the project’s original objectives and include any relevant comments on factors affecting this.

| Objective | Not achieved | Partially achieved | Fully achieved | Comments |
| --- | --- | --- | --- | --- |
| 1. Environmental and conservation Awareness |  |  | √ |  |
| 2. Establish Environmental Conservation Day |  |  | √ |  |
| 3. Introduce Agro forestry |  |  | √ |  |

- Please explain any unforeseen difficulties that arose during the project and how these were tackled (if relevant).

There were lot of controversies that came up during the project period; one has to deal with way and procedures through which the Central government declared the East Nimba Nature Reserve as protected area, especially when it was passed through an act of legislature. The community believe that they were not fully informed and fully consulted in the reserve establishment, as a result, they have been ignore whenever they request for their compensations or incentives that they can depend on as an alternative source of livelihood supports. This friction between the community and the Central government became a huge debate in every quarters of the communities around the reserve, thus making them to become very stubborn and not will to discussed further any matter pertaining to the reserve: whether conservation or protection. Youth were also threaten by their parents to disengage any kind of gathering that had to centre around the reserve until their concerns can be addressed by the central government. Even though, the project focuses were to design and implement a conservation and environmental education outreach program for youths, we were oblige to begin engaging the elderly first through town hall and one- to- one meetings, as a strategy to allow their youths to work with us while advocating for their request to central government.

After several consultative meeting with the elderly and parents of the youth, we finally succeeded in getting the approval for their children participation into the project. We also continue engaging the central government, constructively advocating for the request of the reserve communities to be looked into with serious consideration. Our message to the central government was that, the community are the direct custodian of the reserve and in order to achieve its sustainable management, the community’s must be seen as potential partner with ownership and not as stranger.

## Briefly describe the three most important outcomes of your project.

The three most important outcomes of our project are:

1). Increase environmental conservation awareness among youth. SADS conducted environmental conservation awareness in six communities focusing on rural youth about the importance of conserving the East Nimba Nature Reserve. These awareness activities were conducted in Yolowee, Zortapa, Geipa, Bassa Village, Zorgowee and Zoalay communities in the Gbelay- Geh district, Nimba County, in the form of focus group

discussion, town hall meetings, schools visitation and community youth forums. This is the only activity that continues throughout the life span of the project. SADS field team visited six community’s schools in six communities, and raise environmental and conservation awareness with the participation of over 5,000 youths and children.

2). Established Environmental Conservation Day. SADS negotiated with youths from the six project communities to designate two days for youth environmental conservation social interactions. The first day was organized in April 2008 and was grace with open theatre (traditional song and dances); the second day took place in January 2009 and was also grace with sporting tournament (soccer). During these social interactions, environmental and conservation messages were feature throughout and the Open Theatres was used to stimulate opened dialogue on threats to the East Nimba Nature Reserve and how youths could play a leading role in its mitigations. The total of six communities participated in the one day soccer tournament which was held in the district capital, Zorgowee town. At the end of the tournament, Zortapa community came out as first winner and was presented a trophy.

3). Introduced Agro forestry to youths: SADS worked with youths from each of the six project communities to plant at least 50 seedlings of at least two varieties of wild indigenous fruit tress (Bread fruit and Butter pear tress). The selections of these fruit tress were based on the collective recommendations from the youths, school science teachers and the Forestry Development Authority park staff. This initiative was generally accepted and embraced by everyone in the participated communities because its demonstrated that young people should not only be seen as increasing pressure on natural resource base, but they can contributes greatly to cultivation of those wild plants and animal species that support life forms, especially human beings. Today, science school teachers request their student on monthly bases to plant one tree on the school vicinity.

## Briefly describe the involvement of local communities and how they have benefitted from the project (if relevant).

Soliciting community involvement, participation and ownership are the most important element all of our community interventions and projects try to achieved, because this is the hawk mark of sustainability. The involvement of local communities begun from the very first date we enter them, they had be educated about the concept of the project and what they stand to benefit in the short, medium and long run, most especially when the question of community’s participation and benefit pertaining the reserve establishment were under discussions.

There are many benefits that can be highlighted for the local communities that this project delivered:

- Education: Through this project, many locals especially youths and children can live in harmony with nature, leaving them very healthy. They now know that protect the environment and conserving the park will attract developments and raised income for immediate communities through tourism, community forestry, etc.

- Fruit trees: The fruit trees planted will benefit the communities in the long- run, as they will harvest the fruit for consumption and marketing, while on the other hand those trees will significantly contribute to climate change and covering of degraded land.

## Are there any plans to continue this work?

Yes, there plans to continue the environmental and conservation outreached program targeting youths. This brings us to the next phase where we anticipate on developing a broader and comprehensive strategy for youths participation into environmental and conservation education throughout Liberia. With this on mind, SADS Director has negotiated with a United States organization based in Washington DC know as Advocacy project to send two graduate student under the fellowship for peace program as fellows in this summer to work along with SADS staff in designing this strategy. The open call for fellows are currently posted on their website and be found on www.advocacyproject.org.

The Advocacy Project (AP) is a not-for-profit nongovernmental human rights organization based in Washington, DC, with a field office in Kampala, Uganda. It mission is to produce social change by helping advocates for marginalized communities become catalysts for social justice and claim their rights.

However, this will mark a significant follow- up approach incorporating lesson learns from this initial pilot project.

## How do you plan to share the results of your work with others?

Upon RSG approval, SADS intend to distribute a copy of this report to project communities, Environmental NGOs and other national and local stakeholders, while a copy will also be posted on our website when constructed. We are also open for RSG to post a copy of this report on the RSG website for public information.

## Timescale: Over what period was the RSG used? How does this compare to the anticipated or actual length of the project?

AS budgeted, planned and spelled out in the agreement signed, the RSG funds were used over the period of one year, February 2008- February 2009. The mean that all expenditure made are in line with actual length of the project.

## Budget: Please provide a breakdown of budgeted versus actual expenditure and the reasons for any differences. All figures should be in £ sterling, indicating the local exchange rate used.

| Item | Budgeted Amount | Actual Amount | Difference | Comments |
| --- | --- | --- | --- | --- |
| Staff salaries: |  |  |  |  |
| Project officer | 900 | 900 | 0 | 1person@$75 X 12months |
| Accountant (30%) | 300 | 300 | 0 | 1person@$25 X 12months |
| Environmental and Civil educational Off. | 600 | 600 | 0 | 1person@$50 X12months |
| Equipment: |  |  |  |  |
| Set of video | 175 | 175 | 0 |  |
| Generator (portable) | 150 | 150 | 0 |  |
| Generator Running and Maintenance | 150 | 150 | 0 |  |
| Digital Camera | 175 | 175 | 0 |  |
| Stationeries |  |  |  |  |
| Flip chart | 87.5 | 87.5 | 0 |  |
| Markers | 30 | 30 |  |  |
| Steno pad | 100 | 100 | 0 |  |
| Pen | 12 | 12 | 0 |  |
| Rim of sheet | 25 | 25 | 0 |  |
| Printer ink | 70 | 70 | 0 |  |
| Poster | 100 | 100 | 0 |  |
| T- shirt and printing | 187.5 | 187.5 | 0 |  |
| Transportation |  |  |  |  |
| Internal Transport | 600 | 600 | 0 |  |
| Project inputs Transportation | 250 | 250 | 0 |  |
| Travel expense | 300 | 300 | 0 |  |
| Other |  |  |  |  |
| Workshop & Meeting Costs | 450 | 450 | 0 |  |
| Contingency (5%) | 233.1 | 233.1 | 0 | Used for organizing of sport tournament |
| Bank Charges (including money transfer fees) |  | 77 |  |  |
| Grand total | 4,933 | 5,000 | 77 | Fees charge by bank for receiving the money. |

NB: £sterling to US Dollar (£1.00 = 1.98USD)

- Looking ahead, what do you feel are the important next steps?

The most important next step SADS feel very strong to undertake is to design a national environmental conservation awareness outreached program that will target the involvement of Liberian youths.  The best practices and standards in designing such a program is including the youths and other key actors in the beginning stage through community surveys, meetings, literature reviews and networking. On these bases, Advocacy Project (details are mentioned above) is providing two fellows to work along with SADS staff in this summer to start the designing phase in Liberia. SADS feel very strong that including community’s youth in this process and at the same time using lessons learned from past project will lead to the development of a long- term sustainable planned from youth involvement into protecting and conserving Liberia’s nature heritage for future generations.

## Did you use the RSGF logo in any materials produced in relation to this project? Did the RSGF receive any publicity during the course of your work?

Yes, the RSGF logo was use in the production of T- shirts and posters. These materials were used during workshops, meeting and sporting even for publicity.

## Any other comments?

SADS wish to recognize the numerous contributions and impacts the RSGF have made in helping to environmental and conservation agenda in Liberia. The successful implementation of this small grant act as a catalyst of attracting bigger funds to expand concept and strategies on a larger scale. We at SADS are very grateful for the level of high profile recognition we have received among green NGOs both nationally and internationally.

SADS consider environmental justice as a pivotal point to national peace and development, and we remain committed to this call as we strive to keep Liberia’s nature heritage intact.