Project Update: January- March 2009

Project main goals:

Goal 1: To gather the necessary ecological information to asses the current conservation status of three local endemic species of the family Poeciliidae in western Cuba.

Activities related to goal 1, completed so far:

- 2 Field Trips to Sierra del Rosario Biosphere Reserve (January 5th to 7th (coordination trip) and 25th to 31st to start sampling work (25 % of the sampling trips proposed)

- Establishment of the sampling points.

- Data collection on fish populations and water quality.

- Fish collections for the diet study were also done, but diet analysis will be developed after the second field trip next April.

- Threats identification.

Goal 2: To publish a Pocket Field Guide of Cuban species of this family.

Activities related to goal 2, completed so far:

- We carried out four field trips to other parts of Cuba related to the Field Guide gathering information.

- Pictures collection: 80 % completed.

- Compilation of information: 80 % completed.

- Design of the Field Guide: 20 % completed.

Extra activities carried out thanks to the project:

- Data entrance to the GIS (Geographic Information System) and obtaining preliminary distribution maps of the three Girardinus species in the Sierra del Rosario Biosphere Reserve. This distribution maps have special importance for local conservation actions.

- One talk to conservation workers of the Ecological station located in Sierra del Rosario Biosphere Reserve on local fish diversity and identification basis.